## Worksheet
Task | Owner | Start Date | End Date | Status | Duration (Days) | Dependencies
Project Initiation | Project Manager | 2024-04-01 | 2024-04-07 | Completed | 7
Requirements Gathering | Business Analyst | 2024-04-08 | 2024-04-25 | In Progress | 18 | Project Initiation
Design Phase | UX Designer | 2024-04-26 | 2024-05-10 | Planned | 15 | Requirements Gathering
Development Start | Lead Developer | 2024-05-11 | 2024-06-15 | Not Started | 45 | Design Phase
Testing & QA | QA Lead | 2024-06-16 | 2024-07-05 | Planned | 20 | Development Start
Deployment & Go-Live | DevOps Engineer | 2024-07-06 | 2024-07-10 | Not Started | 5 | Testing & QA
Post-Go-Live Review | Project Manager | 2024-07-11 | 2024-07-15 | Not Started | 5 | Deployment & Go-Live