## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (days) | Status | Dependencies | Milestones | Progress (%) | Risk Level | Resource Allocation | Notes
WFO-001 | Project Initiation & Stakeholder Alignment | Jane Doe | 2024-03-01 | 2024-03-15 | 15 | Completed | None | Alignment Meeting (Day 7) | 100% | Low | Full team | All stakeholders onboarded.
WFO-002 | Scope Definition & Requirements Gathering | John Smith | 2024-03-16 | 2024-04-05 | 21 | In Progress | WFO-001 | Requirements Finalized (Day 20) | 75% | Medium | Project Manager, Business Analysts | Need feedback from operations team.
WFO-003 | Workflow Design & Process Mapping | Lisa Chen | 2024-04-06 | 2024-05-03 | 38 | Planned | WFO-002 | Process Review (Day 30) | 0% | Medium | Design Team, Process Engineers | Align with current operational workflows.
WFO-004 | Technology Stack Selection & Tooling Setup | Mike Brown | 2024-05-04 | 2024-06-10 | 47 | Scheduled | WFO-003 | Tooling Approval (Day 45) | 0% | High | IT Team, DevOps | Need vendor evaluation and budget approval.
WFO-005 | Pilot Implementation & User Training | Sarah Lee | 2024-06-11 | 2024-07-30 | 60 | Not Started | WFO-004 | Pilot Launch (Day 55) | 0% | Low | End Users, Training Officers | Target group includes department heads.
WFO-006 | Full-Scale Deployment & Monitoring | David Kim | 2024-08-01 | 2024-09-30 | 60 | Not Started | WFO-005 | Go-Live (Day 85) | 0% | High | All Teams, Operations | KPIs to be tracked weekly.
WFO-007 | Performance Review & Optimization | Clara White | 2024-10-01 | 2024-10-31 | 30 | Not Started | WFO-006 | Optimization Review (Day 95) | 0% | Medium | Analytics Team, Leadership | Identify bottlenecks and improve throughput.