## Worksheet
Task | Owner | Start Date | End Date | Status | Progress % | Notes
Project Initiation | Sarah Johnson | 2024-03-01 | 2024-03-15 | Completed | 100% | Finalized project scope and objectives.
Requirements Gathering | Michael Chen | 2024-03-16 | 2024-04-10 | In Progress | 65% | Stakeholder interviews completed; documentation in review.
Design Phase | Lisa Wong | 2024-04-11 | 2024-05-15 | Not Started | 0% | Wireframes and UI mockups to be developed.
Development | David Park | 2024-05-16 | 2024-07-30 | Not Started | 0% | Frontend and backend development scheduled.
Testing & QA | Emma Lee | 2024-08-01 | 2024-08-31 | Not Started | 0% | Unit, integration, and user acceptance testing planned.
Deployment | James Rivera | 2024-09-01 | 2024-09-15 | Not Started | 0% | Live environment deployment with rollback plan.
Post-Deployment Review | Sarah Johnson | 2024-09-16 | 2024-09-30 | Not Started | 0% | Performance and user feedback analysis to be conducted.