## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Progress (%) | Priority | Notes
Project Initiation | Jane Doe | 2024-03-01 | 2024-03-15 | Completed | - | 100% | High | Approved project charter and scope.
Stakeholder Alignment | John Smith | 2024-03-16 | 2024-03-31 | In Progress | Project Initiation | 75% | Medium | Meeting schedule finalized; feedback in progress.
Workflow Design | Lisa Chen | 2024-04-01 | 2024-04-15 | Pending | Stakeholder Alignment | 30% | High | Design mockups under review.
Process Implementation | Mark Taylor | 2024-04-16 | 2024-05-31 | Not Started | Workflow Design | 0% | High | System integration planning.
Training & Rollout | Sarah Kim | 2024-06-01 | 2024-06-30 | Planned | Process Implementation | 0% | Medium | User training sessions scheduled.
Total Tasks | 5 | - | - | - | - | - | - | -