## Worksheet
Task | Owner | Start Date | End Date th> | Duration (Days) | Budget (USD) | Status | Progress (%)
Project Initiation & Planning | Jane Smith | 2024-03-01 | 2024-03-15 | 15 | 50,000 | Completed | 100%
Market Analysis & Feasibility | Mark Johnson | 2024-03-16 | 2024-04-10 | 35 | 75,000 | In Progress | 65%
Financial Modeling & Budgeting | Sarah Lee | 2024-04-11 | 2024-05-05 | 35 | 90,000 | Pending Start | -
Resource Allocation & Team Setup | David Wong | 2024-05-06 | 2024-05-18 | 13 | 30,000 | Not Started | -
Development & Prototype Build | Alex Chen | 2024-05-19 | 2024-07-15 | 68 | 320,000 | Not Started | -
Testing & Quality Assurance | Lisa Brown | 2024-07-16 | 2024-08-10 | 35 | 65,000 | Not Started | -
Deployment & Go-Live Plan | James Taylor | 2024-08-11 | 2024-09-15 | 35 | 80,000 | Not Started | -
Post-Launch Review & Optimization | Emma Davis | 2024-09-16 | 2024-10-31 | 46 | 55,000 | Not Started | -