## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies
Project Kickoff Meeting | Alex Morgan | 2024-04-01 | 2024-04-01 | Completed | -
Scope Definition & Stakeholder Alignment | Sophia Lee | 2024-04-02 | 2024-04-05 | In Progress | Project Kickoff Meeting
Requirements Gathering Workshop | Jamal Reed | 2024-04-06 | 2024-04-10 | Planned | Scope Definition & Stakeholder Alignment
Design Phase – Wireframes & Mockups | Lena Kim | 2024-04-11 | 2024-04-18 | Not Started | Requirements Gathering Workshop
Development Start – Backend Setup | Raj Patel | 2024-04-19 | 2024-05-10 | Scheduled | Design Phase – Wireframes & Mockups
Frontend Development & Integration | Mia Thomas | 2024-05-11 | 2024-06-05 | Not Started | Development Start – Backend Setup
Testing & Bug Resolution | Ethan Clark | 2024-06-06 | 2024-06-20 | Planned | Frontend Development & Integration
User Acceptance Testing (UAT) | Claire Nguyen | 2024-06-21 | 2024-06-30 | Not Started | Testing & Bug Resolution
Project Sign-off & Delivery | Alex Morgan | 2024-07-01 | 2024-07-01 | Not Started | User Acceptance Testing (UAT)