## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies
Project Initiation | John Doe | 2024-03-01 | 2024-03-07 | Completed | -
Requirements Gathering | Jane Smith | 2024-03-08 | 2024-03-15 | In Progress | Project Initiation
Design Phase | Alex Johnson | 2024-03-16 | 2024-03-25 | Pending | Requirements Gathering
Development | Team A | 2024-03-26 | 2024-04-10 | Not Started | Design Phase
Testing & Quality Control | Sarah Lee | 2024-04-11 | 2024-04-25 | Planned | Development
Deployment & Launch | Mike Brown | 2024-04-26 | 2024-04-30 | Not Started | Testing & Quality Control
Post-Launch Review | All Team Members | 2024-05-01 | 2024-05-05 | Pending | Deployment & Launch