## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Progress (%)
Project Initiation & Stakeholder Alignment | Sarah Johnson | 2024-03-01 | 2024-03-15 | Completed | - | 100
Workflow Audit & Process Mapping | Michael Chen | 2024-03-16 | 2024-04-05 | In Progress | Project Initiation | 65
Process Redesign & Optimization Framework | Emma Rodriguez | 2024-04-06 | 2024-05-10 | Planned | Workflow Audit | 0
Pilot Implementation in Department A | David Kim | 2024-05-11 | 2024-06-15 | Not Started | Process Redesign | 0
Full-Scale Rollout & Training | Linda Patel | 2024-06-16 | 2024-08-31 | Scheduled | Pilot Implementation | 0
Post-Implementation Review & KPI Analysis | James Wilson | 2024-09-01 | 2024-10-15 | Not Started | Full-Scale Rollout | 0