## Worksheet
Task | Owner | Start Date | End Date | Status | Duration (Days) | Dependencies
Project Initiation | Manager A | 2024-03-01 | 2024-03-07 | Completed | 7 | -
Scope Definition | Manager B | 2024-03-08 | 2024-03-15 | In Progress | 8 | Project Initiation
Requirements Gathering | Team Lead C | 2024-03-16 | 2024-03-25 | Planned | 10 | Scope Definition
Design Phase | Designer D | 2024-03-26 | 2024-04-10 | Not Started | 15 | Requirements Gathering
Development Phase | Dev Lead E | 2024-04-11 | 2024-05-15 | Planned | 35 | Design Phase
Testing & QA | QA Manager F | 2024-05-16 | 2024-06-05 | Not Started | 20 | Development Phase
Deployment Plan | Operations G | 2024-06-06 | 2024-06-15 | Planned | 10 | Testing & QA
Post-Deployment Review | Manager A | 2024-06-16 | 2024-06-25 | Not Started | 10 | Deployment Plan