## Worksheet
Month | Phase | Key Activities | Responsible Team | Start Date | End Date | Status
January | Initiation & Planning | Define project scope, stakeholder alignment, risk assessment | Project Office | 01/01/2024 | 01/31/2024 | On Track
February | Requirements Gathering | Conduct workshops, document user requirements, validate with stakeholders | Product & UX Team | 02/01/2024 | 02/28/2024 | On Track
March | Design & Prototyping | Develop wireframes, interactive prototypes, usability testing | Design Team | 03/01/2024 | 03/31/2024 | On Track
April | Development & Build | Implement features, integrate APIs, conduct code reviews | Engineering Team | 04/01/2024 | 04/30/2024 | On Track
May | Testing & Quality Assurance | Perform unit, integration, and user acceptance testing | QA Team | 05/01/2024 | 05/31/2024 | On Track
June | Deployment & Go-Live | Deploy to production, conduct post-launch monitoring, train users | Operations & Support | 06/01/2024 | 06/30/2024 | On Track