## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Key Deliverables | Status | Dependencies
Initiation | 01/01/2024 | 03/15/2024 | Project Steering Committee | Feasibility Study, Business Case, Stakeholder Analysis | Completed | None
Planning & Design | 03/16/2024 | 06/30/2024 | Product & Engineering Team | Process Flow Diagrams, Workflow Blueprint, Risk Assessment | In Progress | Initiation Phase Complete
Development & Testing | 07/01/2024 | 10/31/2024 | Engineering, QA Team | Beta Version, Unit & Integration Tests | Pending Start | Design Approval Received
Deployment & Rollout | 11/01/2024 | 12/31/2024 | Operations & Customer Support | Pilot Launch, Full-Organization Rollout Plan | Not Started | Development Testing Complete
Post-Implementation Review | 01/01/2025 | 02/28/2025 | Project Office & Leadership Team | Performance Metrics Report, Optimization Recommendations | Not Started | Deployment Complete
Workflow Optimization Project Timeline – Multi Page Template