## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies
Project Kickoff Meeting | Project Manager | 2024-03-15 | 2024-03-15 | Completed | None
Requirements Gathering | Business Analysts | 2024-03-16 | 2024-03-31 | In Progress | Kickoff Meeting
Design Phase | UX/UI Team | 2024-04-01 | 2024-04-15 | Planned | Requirements Gathering
Development Phase | Development Team | 2024-04-16 | 2024-05-31 | Not Started | Design Phase
Testing & QA | QA Team | 2024-06-01 | 2024-06-15 | Planned | Development Phase
Deployment | IT Operations | 2024-06-16 | 2024-06-18 | Not Started | Testing & QA
Post-Launch Review | Project Manager | 2024-06-19 | 2024-06-19 | Planned | Deployment