## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | Completed | None
Requirement Gathering | Business Analyst | 2024-03-16 | 2024-04-10 | In Progress | Project Initiation
Design Phase | UI/UX Designer | 2024-04-11 | 2024-05-05 | Pending | Requirement Gathering
Development Phase | Development Team | 2024-05-06 | 2024-07-15 | Not Started | Design Phase
Testing & QA | QA Engineer | 2024-07-16 | 2024-08-10 | Not Started | Development Phase
Deployment & Go-Live | IT Operations | 2024-08-11 | 2024-08-15 | Not Started | Testing & QA
Post-Deployment Review | Project Manager | 2024-08-16 | 2024-08-20 | Not Started | Deployment & Go-Live