## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies
Project Initiation | John Doe | 2024-03-01 | 2024-03-15 | Completed | -
Requirements Gathering | Jane Smith | 2024-03-16 | 2024-04-10 | In Progress | Project Initiation
Design Phase | Alex Johnson | 2024-04-11 | 2024-05-15 | Not Started | Requirements Gathering
Development Phase | Team A | 2024-05-16 | 2024-07-31 | Not Started | Design Phase
Testing & QA | Lisa Brown | 2024-08-01 | 2024-08-31 | Not Started | Development Phase
Deployment & Launch | Mark Lee | 2024-09-01 | 2024-09-15 | Not Started | Testing & QA