## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Duration (Days)
Project Initiation | 2024-03-01 | 2024-03-07 | Maria Lopez | Completed | 7
Requirements Gathering | 2024-03-08 | 2024-03-21 | David Chen | In Progress | 14
Design Phase | 2024-03-22 | 2024-04-05 | Sarah Kim | Planned | 14
Development & Coding | 2024-04-06 | 2024-05-10 | James Wilson | Not Started | 35
Testing & Quality Assurance | 2024-05-11 | 2024-05-31 | Lisa Thompson | Not Started | 21
Deployment & Go-Live | 2024-06-01 | 2024-06-05 | Robert Brown | Planned | 5
Post-Deployment Review | 2024-06-06 | 2024-06-10 | Team Lead | Not Started | 5