## Worksheet
Task | Responsible Party | Start Date | End Date | Status | Dependencies
Project Initiation & Stakeholder Alignment | Project Manager | 01/03/2024 | 01/10/2024 | Completed | None
Requirements Gathering & Analysis | Business Analysts | 01/11/2024 | 02/05/2024 | Initiation Phase | Project Initiation & Stakeholder Alignment
Design Phase (Wireframes, Prototypes) | UX/UI Team | 02/06/2024 | 03/05/2024 | In Progress | Requirements Gathering & Analysis
Development & Coding | Software Developers | 03/06/2024 | 05/15/2024 | Planned | Design Phase (Wireframes, Prototypes)
Testing & Quality Assurance | QA Team | 05/16/2024 | 06/10/2024 | Not Started | Development & Coding
Deployment & Go-Live | DevOps Team | 06/11/2024 | 06/15/2024 | Planned | Testing & Quality Assurance
Post-Implementation Review & Feedback | Project Manager & Stakeholders | 06/16/2024 | 06/30/2024 | Not Started | Deployment & Go-Live