## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Progress (%)
Project Kickoff Meeting | Project Manager | 2024-04-01 | 2024-04-01 | Completed | - | 100
Requirements Gathering | Business Analyst | 2024-04-02 | 2024-04-15 | In Progress | Kickoff Meeting | 65
Design Phase | UX Designer | 2024-04-16 | 2024-05-05 | Planned | Requirements Gathering | 0
Development Start | Lead Developer | 2024-05-06 | 2024-06-30 | Not Started | Design Phase | 0
Testing & Quality Assurance | QA Lead | 2024-07-01 | 2024-07-31 | Not Started | Development Start | 0
Deployment & Go-Live | DevOps Engineer | 2024-08-01 | 2024-08-05 | Not Started | Testing & QA | 0
Post-Implementation Review | Project Manager | 2024-08-06 | 2024-08-10 | Not Started | Deployment & Go-Live | 0