## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Remarks
Project Kickoff Meeting | Project Manager | 2024-03-01 | 2024-03-02 | Completed | None | Finalize project scope and objectives.
Requirements Gathering | Business Analyst | 2024-03-03 | 2024-03-15 | In Progress | Kickoff Meeting | Collect stakeholder input and document requirements.
Design Phase | UX Designer | 2024-03-16 | 2024-03-31 | Not Started | Requirements Finalized | Create wireframes and user flows.
Development Phase | Software Developers | 2024-04-01 | 2024-05-15 | Not Started | Design Phase Completed | Implement frontend and backend features.
Testing & QA | QA Engineer | 2024-05-16 | 2024-05-30 | Not Started | Development Completed | Perform unit, integration, and user acceptance testing.
Deployment | DevOps Engineer | 2024-06-01 | 2024-06-03 | Not Started | Testing Completed | Deploy to production environment.
Post-Deployment Review | Project Manager | 2024-06-04 | 2024-06-05 | Not Started | Deployment Completed | Gather feedback and document lessons learned.