## Worksheet
Task | Start Date | End Date | Responsible | Status
Project Initiation | 2024-01-01 | 2024-01-15 | John Doe | Completed
Requirements Gathering | 2024-01-16 | 2024-02-14 | Jane Smith | In Progress
Design Phase | 2024-02-15 | 2024-03-31 | Alex Chen | Planned
Development | 2024-04-01 | 2024-06-30 | Team A | Not Started
Testing & QA | 2024-07-01 | 2024-08-15 | Maria Lopez | Not Started
Deployment | 2024-08-16 | 2024-08-31 | IT Support Team | Not Started
Post-Launch Review | 2024-09-01 | 2024-09-15 | Project Manager | Not Started