## Worksheet
Task | Owner | Start Date | End Date | Status
Project Kickoff Meeting | Jane Smith | 2024-03-01 | 2024-03-01 | Completed
Market Research | Mark Johnson | 2024-03-02 | 2024-03-15 | In Progress
Product Design | Lisa Chen | 2024-03-16 | 2024-04-10 | Not Started
Development Phase | Team A | 2024-04-11 | 2024-05-30 | Planned
Testing & QA | David Brown | 2024-06-01 | 2024-06-20 | Not Started
Launch Preparation | Sarah Wilson | 2024-06-21 | 2024-07-15 | Planned
Post-Launch Review | Jane Smith | 2024-07-16 | 2024-07-31 | Not Started