## Worksheet
Task | Responsible | Start Date | End Date | Status | Duration (Days)
Project Initiation | Project Manager | 2024-03-01 | 2024-03-07 | Completed | 7
Scope Definition | Business Analyst | 2024-03-08 | 2024-03-15 | In Progress | 8
Resource Allocation | HR & Ops Lead | 2024-03-16 | 2024-03-22 | Not Started | 7
Risk Assessment | Risk Officer | 2024-03-23 | 2024-03-30 | Planned | 8
Design & Prototyping | UX Designer | 2024-04-01 | 2024-04-15 | Scheduled | 15
Development Phase | Development Team | 2024-04-16 | 2024-05-31 | Not Started | 46
Testing & QA | QA Lead | 2024-06-01 | 2024-06-15 | Planned | 15
Deployment Planning | DevOps Manager | 2024-06-16 | 2024-06-30 | Not Started | 15
Go-Live & Launch | Project Manager | 2024-07-01 | 2024-07-10 | Planned | 10
Post-Launch Review | Stakeholders | 2024-07-11 | 2024-07-15 | Not Started | 5