## Worksheet
Task | Responsible Team | Start Date | End Date | Status | Dependencies | Notes
Project Initiation | Project Office | 2024-03-01 | 2024-03-15 | Completed | - | Finalized project scope and goals.
Requirement Gathering | Product Team | 2024-03-16 | 2024-04-10 | In Progress | Project Initiation | Stakeholder interviews scheduled.
Design Phase | UX & UI Team | 2024-04-11 | 2024-05-05 | Not Started | Requirement Gathering | Wireframes and prototypes to be shared.
Development | Engineering Team | 2024-05-06 | 2024-07-15 | Not Started | Design Phase | Sprint planning and tech stack finalization.
Testing & QA | QA Team | 2024-07-16 | 2024-08-10 | Not Started | Development | Bug tracking and regression testing.
Deployment & Launch | Operations Team | 2024-08-11 | 2024-08-15 | Not Started | Testing & QA | Go-live with monitoring and backup plans.
Post-Launch Review | Project Office | 2024-08-16 | 2024-08-20 | Not Started | Deployment & Launch | Gather feedback and update documentation.