## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Project Initiation | John Smith | 2024-03-01 | 2024-03-15 | Completed | 100% | - | Finalized project scope and budget.
Requirements Gathering | Jane Doe | 2024-03-16 | 2024-04-10 | In Progress | 75% | Project Initiation | Stakeholder interviews completed; documentation in draft.
Design Phase | Mike Johnson | 2024-04-11 | 2024-05-05 | Planned | 0% | Requirements Gathering | UI/UX wireframes to be reviewed.
Development | Sarah Lee | 2024-05-06 | 2024-07-15 | Not Started | 0% | Design Phase | Backend and frontend coding begins post-design approval.
Testing & QA | David Kim | 2024-07-16 | 2024-08-10 | Delayed | 30% | Development | Bug fixes required; testing postponed due to scope changes.
Deployment | Lisa Wong | 2024-08-11 | 2024-08-30 | On Hold | 0% | Testing & QA | Waiting on final sign-off from stakeholders.