## Worksheet
Task | Owner | Status | Due Date | Priority | Progress (%) | Dependencies
Define Workflow Process Map | Jane Doe | In Progress | 2024-03-15 | High | 65% | Requirement Gathering
Identify Key Stakeholders | John Smith | Completed | 2024-02-28 | Medium | 100%
Optimize Approval Workflows | Lisa Chen | Pending | 2024-04-10 | High | 0% | Process Map Complete
Conduct Stakeholder Review Meeting | Team Lead | Scheduled | 2024-03-25 | Medium | 0% | Approval Workflow Draft
Implement Automated Notifications | Mike Ross | Not Started | 2024-05-01 | High | 0% | Workflow Optimization Approved