## Worksheet
Project Name | Phase | Start Date | End Date | Responsible Team | Status | Progress (%) | Key Deliverables | Dependencies | Risk Level
Product Launch Q3 | Planning | 2024-07-01 | 2024-08-15 | Product & UX Team | On Track | 75% | Market Research, MVP Design | Design Approval Pending | Low
Customer Onboarding System | Development | 2024-07-10 | 2024-10-30 | Engineering & Support Team | In Progress | 50% | API Integration, User Portal | Data Migration Phase | Medium
Sales Analytics Dashboard | Testing | 2024-08-01 | 2024-09-30 | Data Science & IT Team | Testing Phase | 85% | Performance Reports, User Export | Third-Party API Sync | Low
Marketing Campaign 2024 | Execution | 2024-07-15 | 2024-11-30 | Marketing & Content Team | Scheduled | 30% | Social Ads, Email Sequences | Budget Approval Pending | High