## Worksheet
Task ID | Task Name | Owner | Assigned Date | Due Date | Status | Priority | Progress % | Next Review Date | Notes
WFO-001 | Requirement Gathering Phase | John Smith | 2024-03-15 | 2024-04-10 | In Progress | High | 65% | 2024-04-01 | Stakeholder interviews scheduled; finalize scope document.
WFO-002 | UI/UX Design Finalization | Sarah Lee | 2024-03-20 | 2024-04-15 | Pending | Medium | 40% | 2024-04-05 | Design mockups approved by product lead; feedback loop ongoing.
WFO-003 | Backend Development Kickoff | Michael Chen | 2024-03-25 | 2024-05-01 | Not Started | High | 0% | 2024-04-15 | Database schema defined; API endpoints under review.
WFO-004 | QA Testing & Validation | Linda Park | 2024-04-10 | 2024-05-10 | On Hold | Medium | 20% | 2024-04-25 | Dependency on frontend completion; waiting for final design handoff.
WFO-005 | Deployment Planning | David Kim | 2024-04-15 | 2024-05-30 | In Progress | Low | 50% | 2024-05-10 | Infrastructure setup complete; rollback strategy drafted.