## Worksheet
Project Name | Team Member | Start Date | End Date | Status | Progress (%) | Milestone Achieved | Next Action | Risk Level
Product Launch Phase 1 | Sarah Johnson | 2024-03-01 | 2024-04-30 | On Track | 85% | UI Design Finalized | Finalize backend integration | Low
Customer Onboarding System | James Lee | 2024-03-15 | 2024-05-15 | In Progress | 40% | Requirement Gathering Complete | Develop prototype | Medium
Marketing Campaign Rollout | Maria Garcia | 2024-03-20 | 2024-04-15 | Completed | 100% | Launch Successful | Review performance metrics | Low
QA Process Enhancement | David Kim | 2024-03-10 | 2024-05-31 | Planned | 0% |  | Initiate scope review | High