## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%) | Notes
Define Workflow Goals | Jane Doe | 2024-04-10 | In Progress | High | 60% | Align with business objectives and stakeholder feedback.
Map Current Process Flows | John Smith | 2024-04-15 | Pending | Medium | 30% | Conduct interviews and document existing steps.
Identify Bottlenecks & Delays | Lisa Chen | 2024-04-20 | Not Started | High | 0% | Analyze cycle times and feedback loops.
Propose Optimized Workflow | Michael Brown | 2024-05-01 | In Progress | High | 45% | Draft new process with automation suggestions.
Review & Stakeholder Feedback | Team Lead | 2024-05-10 | Scheduled | Medium | 10% | Schedule meetings with department heads.
Implement Changes & Monitor | Jane Doe | 2024-06-15 | Not Started | High | 0% | Roll out new workflow and track KPIs.