## Worksheet
Task | Owner | Due Date | Status | Progress (%) | Notes
Project Kickoff Meeting | John Smith | 2023-10-05 | Completed | 100% | All stakeholders aligned on goals.
Scope Finalization | Sarah Lee | 2023-10-12 | In Progress | 75% | Final review pending from legal team.
Resource Allocation | Michael Brown | 2023-10-18 | Pending | 0% | Waiting for budget approval.
Risk Assessment Report | Linda Wong | 2023-10-25 | Not Started | 0% | Initial draft scheduled for next week.
Stakeholder Review Session | Team Lead | 2023-11-03 | Not Started | 0% | To be scheduled after scope approval.