## Worksheet
Task | Owner | Status | Due Date | Priority | Progress (%) | Notes
Requirement Gathering | Alex Johnson | In Progress | 2024-04-15 | High | 65% | Client feedback collected; final scope pending approval.
UI/UX Design Finalization | Sophie Chen | Pending | 2024-04-25 | High | 30% | Design reviews scheduled for next week.
Backend Development | Marcus Reed | Not Started | 2024-05-10 | Critical | 0% | API architecture under review.
Testing & QA | Taylor Brooks | Not Started | 2024-05-30 | Medium | 0% | Will begin after backend is complete.
Deployment & Launch | Nina Patel | Not Started | 2024-06-15 | High | 0% | Post-launch monitoring and reporting setup.