## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies | Notes
Requirements Gathering | Jane Smith | 2024-03-01 | 2024-03-15 | In Progress | High | None | Initial stakeholder interviews scheduled.
Design Phase | Alex Chen | 2024-03-16 | 2024-04-10 | Planned | High | Requirements Gathering Complete | Wireframes and user flows to be finalized.
Development | Team A | 2024-04-11 | 2024-06-30 | Not Started | Critical | Design Phase Complete | Frontend and backend modules to be built.
Testing | QA Team | 2024-07-01 | 2024-07-20 | Not Started | High | Development Complete | Unit, integration, and UAT testing.
Deployment | Ops Team | 2024-07-21 | 2024-07-25 | Not Started | Medium | Testing Complete | Staging to production rollout.
Post-Deployment Review | Project Manager | 2024-07-26 | 2024-07-30 | Not Started | Low | Deployment Complete | Gather feedback and update documentation.