## Worksheet
Workflow Stage | Responsible Team | Start Date | End Date | Status | Priority | Progress %
Requirement Gathering | Product & UX Team | 2024-03-01 | 2024-03-15 | On Track | High | 85%
Design & Prototyping | Design Team | 2024-03-16 | 2024-04-05 | In Progress | Medium | 60%
Development | Engineering Team | 2024-04-06 | 2024-05-15 | Pending Start | High | 0%
Testing & QA | QA Team | 2024-05-16 | 2024-06-10 | Not Started | High | 0%
Deployment & Launch | Ops & PM Team | 2024-06-11 | 2024-06-15 | Planned | Critical | 0%