## Worksheet
Task | Assigned To | Start Date | End Date | Status | Priority | Notes
Requirement Gathering | Jane Doe | 2024-04-01 | 2024-04-10 | In Progress | High | Engage stakeholders to define key business needs.
Process Mapping | John Smith | 2024-04-11 | 2024-04-15 | Pending | Medium | Create visual flowcharts of current workflows.
Workflow Design | Alex Johnson | 2024-04-16 | 2024-05-05 | Planned | High | Propose optimized process with automation points.
Stakeholder Review | Team Lead | 2024-05-06 | 2024-05-10 | Scheduled | High | Present design for feedback and approval.
Implementation Plan | Sarah Lee | 2024-05-11 | 2024-06-30 | Not Started | Critical | Develop detailed execution roadmap and timelines.