## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Resource Allocation | Priority Level | Milestones
Workflow Assessment | Sarah Thompson | 2024-04-01 | 2024-04-10 | 10 | In Progress | None | Project Team A | High | Phase 1 Initiated
Process Mapping | David Chen | 2024-04-11 | 2024-04-25 | 15 | Planned | Workflow Assessment Complete | Project Team B | High | Process Diagram Ready
Identify Bottlenecks | Lisa Rodriguez | 2024-04-26 | 2024-05-05 | 10 | Pending | Process Mapping Complete | Analytics Team | Medium | Bottleneck Report Due
Optimize Workflow Paths | James Wilson | 2024-05-06 | 2024-05-25 | 20 | Planned | Bottlenecks Identified | Project Team A & B | High | Path Optimization Finalized
Training & Documentation | Elena Kim | 2024-05-26 | 2024-06-15 | 20 | Not Started | Optimization Complete | All Teams | Medium | Training Sessions Scheduled
Post-Implementation Review | Michael Brown | 2024-06-16 | 2024-06-30 | 15 | Planned | Training Completed | Project Leadership Team | High | Review Report Submitted