## Worksheet
Workflow Optimization Schedule Planner - Extended
Project Phase | Start Date | End Date | Responsible Team | Status | Key Deliverables | Risk Assessment (High/Medium/Low)
Discovery & Requirement Gathering | 2024-03-01 | 2024-03-15 | Product & Business Analysis Team | On Track | Stakeholder interviews, requirement doc v1.0, workflow maps | Medium
Process Mapping & Workflow Design | 2024-03-16 | 2024-04-05 | Design & Engineering Team | In Progress | Workflow diagrams, user journey maps, process flows v1.1 | Low
Stakeholder Validation & Feedback Loop | 2024-04-06 | 2024-04-18 | Product & UX Team | Pending Review | Feedback summary report, revised design mockups | High
Development & Implementation Phase | 2024-04-19 | 2024-06-30 | Engineering Team (Backend & Frontend) | Not Started | Module builds, API integrations, system testing plan | High
Testing & Quality Assurance | 2024-07-01 | 2024-07-31 | QA & Operations Team | Not Started | End-to-end testing reports, bug resolution logs | Moderate
Deployment & Go-Live Planning | 2024-08-01 | <2024-08-15 | Operations & IT Team | Not Started | Go-live checklist, user training materials, rollback plan | Low
Post-Launch Monitoring & Optimization | 2024-08-16 | Ongoing | Analytics & Support Team | Not Started | Performance dashboards, user feedback loop, optimization reports | Moderate