## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Notes
Requirement Gathering | Jane Smith | 2024-03-01 | 2024-03-15 | Completed | High | Stakeholder interviews completed; documented requirements finalized.
Workflow Design | Mike Johnson | <2024-03-16 | 2024-03-31 | In Progress | Medium | Finalizing process flow diagrams; feedback from product team pending.
System Integration | Sarah Lee | 2024-04-01 | 2024-04-15 | Planned | High | Integration with legacy system under development; API testing scheduled.
User Training | David Chen | 2024-04-20 | 2024-04-30 | Completed | Low | Training sessions conducted for 5 departments; materials archived.
Performance Review | Team Lead | 2024-05-01 | 2024-05-10 | Pending | High | Evaluate efficiency metrics; identify bottlenecks in current workflow.