## Worksheet
Date | Task | Owner | Duration (hrs) | Status | Priority | Next Action
2024-04-01 | Review workflow processes | John Doe | 4 | In Progress | High | Schedule team meeting on 2024-04-05
2024-04-03 | Identify bottlenecks | Jane Smith | 6 | Pending | Medium | Share data with operations team by 2024-04-05
2024-04-06 | Optimize approval workflow | Mike Johnson | 8 | Not Started | High | Finalize draft changes by 2024-04-08
2024-04-10 | Conduct pilot test | Lisa Brown | 5 | Planned | Medium | Collect feedback and report by 2024-04-12
2024-04-15 | Implement changes across departments | Team Lead | 10 | Not Started | Critical | Coordinate rollout with department heads
Workflow Optimization – Schedule Planner ¦ Report Version