## Worksheet
Task | Owner | Start Date | End Date | Status | Duration (Days) | Priority
Requirement Gathering | Jane Smith | 2024-04-01 | 2024-04-15 | Completed | 15 | High
Design Phase | Mark Johnson | 2024-04-16 | 2024-05-10 | In Progress | 35 | High
Development Phase | Team A | 2024-05-11 | 2024-07-15 | Not Started | 65 | Medium
Testing & QA | Lisa Chen | 2024-07-16 | 2024-08-10 | Not Started | 35 | High
Deployment & Launch | Alex Rivera | 2024-08-11 | 2024-08-15 | Not Started | 5 | Critical