## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Notes
Requirement Gathering | Jane Smith | 2024-03-01 | 2024-03-10 | Completed | - | Initial stakeholder interviews conducted.
Workflow Design | Mark Johnson | 2024-03-11 | 2024-03-25 | In Progress | Requirement Gathering | Draft flow diagrams reviewed by product team.
Process Validation | Lisa Chen | 2024-03-26 | 2024-04-05 | Planned | Workflow Design | Testing with pilot users scheduled.
Implementation Phase | Team A | 2024-04-06 | 2024-05-15 | Not Started | Process Validation | Integration with existing CRM system.
Training & Onboarding | Sarah Kim | 2024-05-16 | 2024-05-31 | Not Started | Implementation Phase | Develop training materials and conduct sessions.