## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies
Requirement Gathering | Jane Doe | 2024-03-15 | 2024-03-25 | Completed | 100% | -
Design Phase | John Smith | 2024-03-26 | 2024-04-10 | In Progress | 65% | Requirement Gathering
Development | Alex Chen | 2024-04-11 | 2024-05-15 | Pending | 0% | Design Phase
Testing & QA | Sarah Kim | 2024-05-16 | 2024-05-31 | Not Started | 0% | Development
Deployment | Michael Brown | 2024-06-01 | 2024-06-05 | Planned | 0% | Testing & QA