## Worksheet
Task | Responsible Party | Due Date | Priority | Status | Notes
Define Workflow Goals | Project Manager | 01/05/2024 | High | Not Started | Align team objectives with business outcomes.
Map Current Workflow | Operations Lead | 01/12/2024 | High | In Progress | Document all steps and bottlenecks.
Identify Process Gaps | Process Analyst | 02/01/2024 | Medium | Not Started | Analyze inefficiencies using data and feedback.
Design Optimized Workflow | Product Team | 03/01/2024 | High | Not Started | Include automation, clear roles, and feedback loops.
Conduct Pilot Run | Operations Team | 04/05/2024 | High | Not Started | Test with a small group to validate improvements.
Roll Out Workflow | Executive Sponsor | 05/01/2024 | High | Not Started | Full organization-wide implementation.
Monitor & Evaluate Performance | Analytics Team | Ongoing | Medium | Not Started | Track KPIs and refine based on results.