## Worksheet
Task | Responsible Party | Due Date | Status | Notes/Comments
Define workflow objectives | Project Manager | 2024-04-15 | Completed | Initial goals outlined and approved by stakeholders.
Map current workflow process | Operations Team | 2024-04-20 | In Progress | Process flowchart drafted, awaiting review.
Identify bottlenecks and inefficiencies | Process Analyst | 2024-04-25 | Not Started | Waiting for final process map to be approved.
Propose workflow optimization solutions | Product Team | 2024-05-05 | Not Started | Solutions to be developed based on bottleneck analysis.
Conduct pilot test of optimized workflow | QA & Development Team | 2024-05-15 | Not Started | Pilot will run in test environment for 7 days.
Review results and finalize changes | Project Manager | 2024-05-25 | Not Started | All team feedback gathered before final rollout.