## Worksheet
Task | Responsibility | Due Date | Status | Priority | Notes
Define Workflow Objectives | Project Manager | 2024-04-01 | In Progress | High | Align with business goals and stakeholder needs.
Map Current Process Flows | Operations Team | 2024-04-10 | Pending | High | Use BPMN diagrams to document existing steps.
Identify Bottlenecks and Inefficiencies | Analyst | 2024-04-15 | Pending | Medium | Analyze cycle times and error rates.
Design Optimized Workflow Model | Design Team | 2024-04-25 | Not Started | High | Include automation and real-time tracking.
Conduct Stakeholder Review | Project Manager | 2024-05-05 | Not Started | High | Gather feedback and refine process.
Implement New Workflow | IT & Operations | 2024-05-15 | Not Started | Critical | Phase-in over 3 weeks with monitoring.
Monitor Performance & Adjust | Operations Team | Ongoing | Ongoing | Medium | Weekly KPI reviews and performance reports.