## Worksheet
Task | Owner | Due Date | Status | Priority
Define workflow objectives | Team Lead | 2024-04-05 | Pending | High
Map current workflow processes | Operations Manager | 2024-04-10 | In Progress | High
Identify bottlenecks and inefficiencies | Process Analyst | 2024-04-15 | Pending | Medium
Propose workflow redesign options | Team Lead | 2024-04-20 | Pending | High
Conduct stakeholder feedback session | Customer Success Team | 2024-04-25 | Pending | Medium
Finalize and document optimized workflow | Operations Manager | 2024-05-02 | Pending | High
Train team on new workflow procedures | HR & Training Coordinator | 2024-05-10 | Pending | Medium