## Worksheet
Task | Responsibility | Due Date | Status | Priority
Define Workflow Objectives | Project Manager | 2023-10-05 | In Progress | High
Map Current Process Flow | Operations Lead | 2023-10-10 | Not Started | High
Identify Bottlenecks and Delays | Data Analyst | 2023-10-15 | Not Started | Medium
Propose Process Improvements | Process Engineer | 2023-10-20 | Not Started | High
Conduct Stakeholder Review | Project Manager | 2023-10-25 | Not Started | Medium
Implement New Workflow | IT Team | 2023-11-01 | Not Started | High
Monitor Performance Metrics | Operations Lead | 2023-11-05 | Not Started | Low