## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%)
Define Workflow Objectives | Jane Smith | 2024-03-15 | Completed | High | 100%
Map Current Process Flows | Mark Johnson | 2024-03-20 | In Progress | High | 65%
Identify Bottlenecks | Sarah Lee | 2024-03-25 | Pending | Medium | 0%
Redesign Workflow Steps | David Chen | 2024-04-05 | Not Started | High | 0%
Conduct Stakeholder Review | Team Lead | 2024-04-10 | Completed | Medium | 100%
Implement Automation Tools | Alex Rivera | 2024-04-15 | In Progress | High | 40%