## Worksheet
Workflow Step | Responsibility | Due Date | Status | Lead Time (Days) | Action Required
Stock Receiving | Procurement Team | 01/04/2024 | Completed | 2 | Verify & update inventory master
Stock Verification | Warehouse Manager | 03/04/2024 | Pending | 5 | Conduct physical count and reconciliation
Reordering Trigger | Inventory Analyst | 05/04/2024 | Planned | 3 | Analyze stock levels and generate reorder list
Purchase Order Placement | Procurement Officer | 07/04/2024 | In Progress | 1 | Submit PO to supplier with delivery terms
Delivery & Receipt Confirmation | Logistics Team | 09/04/2024 | Not Started | 7 | Confirm delivery date and update system
Stock Adjustment & Audit | Auditor / Warehouse Manager | 12/04/2024 | Not Started | 10 | Conduct end-of-period audit and adjust records