## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Estimated Time (hrs) | Dependencies | Progress (%) | Notes
T-001 | Project Kickoff Meeting | John Doe | 2024-04-05 | High | In Progress | 2.5 |  | 40% | Confirm stakeholders and agenda.
T-002 | Requirements Gathering | Anna Lee | 2024-04-15 | High | Not Started | 8 | T-001 | 0% | Collect input from key departments.
T-003 | Design Phase Finalization | Michael Chen | 2024-05-10 | Medium | Planned | 6.5 | T-002 | 15% | Finalize wireframes and UI mockups.
T-004 | Development Setup | Lena Park | 2024-05-15 | Low | Not Started | 3 | T-003 | 0% | Configure environments and tools.
T-005 | Testing & Quality Assurance | David Kim | 2024-06-10 | High | Not Started | 12 | T-004 | 0% | Execute unit and integration tests.