## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Assigned To | Estimated Time (hrs) | Progress (%) | Comments
T-001 | Finalize Project Scope Document | Jane Doe | 2024-04-15 | High | In Progress | Marketing Team | 8 | 65% | Need alignment with Product Lead.
T-002 | Conduct Stakeholder Workshop | John Smith | 2024-04-18 | Medium | Pending | Operations Team | 4 | 0% | Awaiting calendar availability.
T-003 | Review Budget Allocation | Lisa Chen | 2024-04-20 | High | Not Started | Finance Department | 6 | 0% | Need access to Q3 forecasts.
T-004 | Draft Risk Mitigation Plan | Mike Brown | 2024-04-25 | Medium | In Progress | Risk Management Team | 5 | 40% | Initial draft completed; awaiting review.
T-005 | Prepare Go-Live Checklist | Sarah Lee | 2024-05-01 | High | Not Started | IT Operations Team | 3 | 0% | Need input from QA team.