## Worksheet
Task ID | Task Name | Assigned To | Priority | Due Date | Status | Progress (%) | Dependencies | Comments | Updated On
T-001 | Requirement Gathering Phase | Alex Morgan | High | 2024-03-15 | In Progress | 60% | T-002, T-003 | Initial stakeholder interviews completed. | 2024-03-10
T-002 | System Architecture Design | Sam Patel | High | 2024-03-25 | Not Started | 0% | T-001 |  | 2024-03-12
T-003 | UI/UX Prototyping | Jordan Lee | Medium | 2024-04-05 | In Progress | 45% | T-001 | Wireframes approved by product team. | 2024-03-18
T-004 | Backend Development | Rahul Singh | High | 2024-04-15 | Not Started | 0% | T-002, T-005 |  | 2024-03-19
T-005 | Testing & QA Plan | Mia Chen | Medium | 2024-05-10 | Not Started | 0% | T-004, T-003 |  | 2024-03-21
Total Tasks |  |  |  |  | 5 | Status Summary